## Saudi
Project Name: Saudi- JCSA Current Sprint:Sprint 28 & 29
Sprint | Feature | Work Item Type | ID | Title | State | Design | Execution Ready | Tested | Test Resource | Internal QA status | Comments
Sprint 28 | Feedback-97084 | User Story | 96030 | Useability - prevent jockey double booking in 1 race | Deployed to Prod | Yes | Yes |  | Hajra Qurban
Sprint 28 | Auctions-97085 | User Story | 101061 | CR - Auction - Default Screens & Tables Required - Phase 2 | QA | Yes | Yes |  | Hajra Qurban
Sprint 28 | Auctions-97085 | User Story | 100446 | Remove Non runners - Horse Performance - API Website | Deployed to Prod | Yes | Yes |  | Hajra Qurban
Sprint 28 | Not linked | User Story | 100406 | Eligibilty Job to Stop working after entries close time passed | QA | N/A | N/A |  | Sheharyar Hanif
Sprint 28 | Feedback-97084 | User Story | 98009 | First Name - Sur Name Date Migration | Deployed to Prod | Yes | Yes |  | Hajra Qurban
Sprint 29 | Auctions-97085 | User Story | 98210 | CR - Re-enable Auction Menu Options on the Owner Portal menu | QA | Yes |  |  | Hamza Bashir
Sprint 29 | Auctions-97086 | User Story | 50928 | CR - FE - Horse Auction - Register Horse | QA | Yes | Yes |  | Aaron King
Sprint 29 | Not linked | User Story | 102893 | Bulk Update Races to show in Result api | QA | Yes | Yes |  | Aaron King
Sprint 29 | Auctions-97086 | User Story | 99362 | CR - Generate a Horse Auction Registration Document | QA | Yes | Yes |  | Aaron King
Sprint 29 | Auctions-97087 | User Story | 99500 | CR - BE - Auction - Administrator Add/Maintain Horse Sale Animals | QA | Yes | Yes |  | Aaron King
nb

## ERA
Project Name: ERA Current :Sprint 27
Work Item Type | ID | Title | State | FBT Design | Execution Ready | Tested | Test Resource | Internal QA status | Comments
User Story | 82022 | BE - Racing - Fill weight out field with weight horse should be carrying | QA | YES | YES |  | Hajra
User Story | 88856 | BE - Vets - Vaccinations - Pick Up the type of vaccination i.e first vaccine or booster | QA | YES | YES |  | Hajra |  | bug 10091
User Story | 88859 | FE - Vets - Vaccinations- PDF version | QA | YES | YES |  | Hajra
User Story | 88926 | JFD REQUIRED -0 FE - Racing - Unable to publish symbols on website | QA | N/A | N/A |  | Hajra |  | Not testable, as Dalia Riad commented Aug 14, there is no UAT version of this website that we can use to test and validate our changes the changes were unit tested from the API code/browser and accordingly the changes were merged to the main branch
User Story | 88943 | BE - Racing - Maiden Race Priorities | QA | YES | YES |  | Hajra
User Story | 90382 | BE - Racing - HORSE FORM - Cloudflow needs updates | QA | N/A | N/A |  | Hajra |  | [SM:8/22/2024]-Non functional,Cloudflow needs updates
User Story | 91211 | FE - WEBSITE - Horse Performance API - Add Grade / Group Level & Max number of wins | QA | N/A | N/A |  | Hajra |  | [SM:8/22/2024]-Non functional, Its implemented on API level.
User Story | 92841 | BE - PCF - NEW 220524 - Stewards PCF Comments control | QA | YES | YES |  | Hajra
User Story | 92843 | FE - Stewards - NEW220524 - Stewards Report - Hide Vet comments / starters comments from automated steward report | UAT Ready | YES | YES |  | Hajra
User Story | 92845 | FE - Stewards - NEW220524 - Stewards Report - Pull embargoes into the base table of the stewards report | UAT Ready | YES | YES |  | Hajra
User Story | 93053 | BE- VETS - NEW 220524 - Bleeders - Vet Reports - Pull into view bleeder history of the horse | QA | YES | YES
User Story | 99344 | BE- Licensing - Emergency contact details on a license form show flow onto the primary contact - NEWLY ADDED 020824 (should have been in scope) | QA | YES | YES |  | Hajra |  | bug 100515
User Story | 99965 | Change to Trainer Preference Logic | QA | YES | YES |  | Hajra
User Story | 92738 | JFD Required - FE - Licensing - NEW 220524WEBSITE / APP - Min Riding weight and Claim to be added to Jockey Profile - website and app | QA | YES | YES |  | Hajra
User Story | 99372 | BE - Vets NEW 220224 - Sampling / Sample Test Results - Raceday Screening - Create Raceday Screening Sample Records - Phase 2 | QA Ready | YES | NO |  | Hajra

## HSI Sprint 11
Project Name:ERA Current Sprint:Sprint 28
Sprint | Feature | Work Item Type | ID | Title | State | Design | Execution Ready | Tested | Test Resource | Comments
Sprint 11 | 1203 - FE- Naming Application | User Story | 2803 | FE - Naming Applications | In QA | Yes | Yes | No | Hajra Qurban
Sprint 11 | 2804 - Prefix Registeration | User Story | 2805 | Prefixes - View, Add & Maintain | In QA | Yes | Yes | No | Hajra Qurban
Sprint 11 | 1201 - DNA Submission & Result Files | User Story | 3210 | Printing Labels - facility to batch print the DNA labels | Ready for QA | Yes | Yes | No | Hajra Qurban
Sprint 11 | 1184- Data Migration- ALM | User Story | 4292 | Data Migration : Classification History table | Ready for QA | Non- Functional / Not qualify for design | Yes | No | Hajra Qurban | Comments have been added to avoid assigning such user stories to test engineer
Sprint 11 | 2801- Microchip Management | User Story | 4642 | Microchip Management - Status View | Ready for QA | Yes | Yes | No | Hajra Qurban
Sprint 11 | 4633-Case Management | User Story | 4823 | Case Management - Configure Out of the Box 'Case Management' | Ready for QA | Yes | Yes | No | Hajra Qurban
Sprint 11 | 1195- BE- View/Maintain Animals | User Story | 3061 | Animal Enquiry - View & Maintain Animal Classification Data | In QA | Yes | Yes | No | Hajra Qurban
nb

## HSI
Project Name: HIS- Horse Sport Ireland Current Sprint:Sprint 9& 10
Feature | Work Item Type2 | ID | Title | State | Design | Execution Ready | Tested | Test Resource | Internal QA status | Comments
FE - Naming Application | User Story | 2803 | FE - Naming Applications | Ready for QA | YES | No
BE - Audits | User Story | 4061 | Audits | Ready for QA | YES | No
FE- Registeration General | User Story | 1336 | Fees - Cater for Volume Discount | Ready for QA | YES | No
BE - View/Maintain Animals | User Story | 3061 | Animal Enquiry - View & Maintain Animal Classification Data | In QA | YES | Yes

## ERA Sprint 28
Project Name:ERA Current Sprint:Sprint 28
Sprint | Feature | Work Item Type | ID | Title | State | Design | Execution Ready | Tested | Test Resource | Internal QA status | Comments
Sprint 28 | 96391- Handicappers | User Story | 92846 | BE - Handicappers - NEW 220524 - Send a comm when a horse changes status to in training | QA | Yes | Yes | No | Hajra Qurban
Sprint 28 | 100987-JFD-Website | User Story | 85188 | JFD REQUIRED - FE - Racing - ADD tek_manually_timed to race / season calendar API -CR | QA | Yes | Yes | No
Sprint 28 | 100987-JFD-Website | User Story | 85009 | JFD Third-Party API Updates | QA | Yes | Yes | No
Sprint 28 | 100987-JFD-Website | User Story | 99428 | JFD - Season Calendar API - Query Parameters | QA
Sprint 28 | 100987-JFD-Website | User Story | 99429 | JFD Required - Horses - Query Parameters | QA
Sprint 28 | 100987-JFD-Website | User Story | 99430 | JFD Required - Users - Query Parameters | QA
Sprint 28 | 100987-JFD-Website | User Story | 99431 | JFD - Fixtures Endpoint - Racecourses - Query Parameters | QA
Sprint 28 | 100987-JFD-Website | User Story | 99857 | JFD Required - Send Pictures in profile pages API | QA | Yes | Yes
Sprint 28 | 100987-JFD-Website | User Story | 99861 | JFD Required - Send seperate turf and dirt runs calculation in Horse Profile API | QA | Yes | Yes
Sprint 28 | 100987-JFD-Website | User Story | 99876 | JFD Required - Ensure account status is in the get users API | QA
Sprint 28 | 101905-Keep Charges | User Story | 101610 | Keep Chartges - Table Change: Trainer History should link with horse owner. Add column in trainer history table. | QA | Yes | Yes
nb